## Slide 1: Course Development Process
Kim Henry

## Slide 2: Objectives
By the end of this session, participants should be able to:
  Describe the three primary aspects of determining the scope of a course.
  Identify the members of a typical course development team and describe the role of each member.
  Identify strategies for organizing project information.
  Relate key activities to course development processes and workflow.

## Slide 3: Defining the Project

## Slide 4: Defining the Project
Clearly state all of the project goals.
Articulate the high-level specifications for the course.
  Scope
      determine overarching, big-picture learning objectives
      identify primary topics
  Sequence
      order the primary topics
      identify and organize second-level sub-topics
  Learning Objectives
      write student-centered, measurable learning objectives for each sub-topic

## Slide 5: Identifying Team Members and Their Roles

## Slide 6: Project Manager
    Create and manage timelines, work assignments and deliverables.
    Keep team members and stakeholders informed on progress.
    Initiate and maintain regular communication with all team members.
    Work with SMEs to develop a course framework.
    Establish course organization.
    Coordinate the implementation of materials into the OLI Platform.

## Slide 7: Course Developer
    Review course materials and ensure proper alignment between objectives, activities and assessments.
    Identify places for and manage the development of activities including unique activities and media.
    Assist in the implementation of materials into the OLI platform.

## Slide 8: Learning Scientist
Consult on learning design.
Produce model for the Learning Dashboard.

## Slide 9: SME/Core Author(s)
Determine course objectives.
Create learning materials that reflect OLI principles
  Expository text
  Activities
  Assessments
Revise materials based on reviewer feedback.
Review and provide feedback on course materials created by other authors.

## Slide 10: SME/Review and Contribute
Review and provide feedback on course materials prepared by core author(s).
Assist in writing assessment questions.
Assist in writing activities.

## Slide 11: Coders
Given completed or nearly completed design documents, implement material into OLI Platform.
Review and make minor edits on material being implemented.
Fix identified errors in xml documents.

## Slide 12: Organizing Project Information

## Slide 13: Course Website
Design Documents
General Information
Resources
Error Report Form
PM/CD Templates

## Slide 14: Developing the Course

## Slide 15: Developing the Course
Develop and Design
    refine learning objectives
    write assessment questions
    write activities
    write expository material
Implement
    code pages and activities
    Integrate images, videos, and other content
Test and Review
    evaluate current implementation of course
    identify changes and corrections

## Slide 16: Developing the Course…

## Slide 18: Have fun… Enjoy the process… May you experience success with your projects!

## Slide 19: STEM Readiness Core Skills Course

## Slide 20: Goal
Produce a 45 hour OLI-STEM Readiness Core Skills Course that will assist participants in identified technical programs in improving the necessary core skills including math, communication and professionalism required to be successful in the programs and ultimately to assist the students in acquiring and maintaining employment in a STEM related career.

## Slide 21: Pathways
Mechatronics
Composites Material Technology
Cyber Technology
Electric Vehicle Technology
Environmental Technology

## Slide 22: Core Skills
    Math
    Communication
    Professionalism
    Contextualized Cased-based Modules
    Integrated topics throughout the course
    The Big Picture of Critical Thinking/Problem Solving incorporated throughout the course.
Course Approach